## Adjusted
EqMSN 2026 per product (Adjusted)
Source: Tableau Avances / Retards export, 07/10/2026. 1 MSN = 1.0, spread evenly over calendar days from first milestone to OTA. 2025 work on MSNs shipping in 2026 is added to their 2026 months.
Produit | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Total
300VU | 0.63 | 0.69 | 0.97 | 0.74 | 0.74 | 0.59 | 0.94 | 0.85 | 1.65 | 1.41 | 1.12 | 0.92 | 11.25
740VU | 7.5 | 3.91 | 3.63 | 3.91 | 3.83 | 3.14 | 2.41 | 2.5 | 3.34 | 3.81 | 3.67 | 3.68 | 45.33
ISSF | 0.52 | 0.47 | 0.02 | 0.73 | 0.77 | 1.15 | 0.94 | 0.42 | 2.8 | 1.93 | 2.27 | 3.33 | 15.35
MDCD | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39 | 1.08 | 0.53 | 0 | 5
MFRL | 25.74 | 20.68 | 31.99 | 29.65 | 26.88 | 25.3 | 22.63 | 23.53 | 33.09 | 41.9 | 39.81 | 35.92 | 357.12
MIP | 15.01 | 7.71 | 7.27 | 6.45 | 6.19 | 5.39 | 5.28 | 5.3 | 6.2 | 7.59 | 7.8 | 8.12 | 88.31
MIP(2) | 3.37 | 1.01 | 0.81 | 0.62 | 0.79 | 0.68 | 0.64 | 0.69 | 0.51 | 0.64 | 0.67 | 0.72 | 11.15
OHP | 2.33 | 0.59 | 0.69 | 0.8 | 0.65 | 0.51 | 0.63 | 0.51 | 0.7 | 0.82 | 0.62 | 0.68 | 9.53
PTVU | 15.03 | 3.32 | 3.76 | 3.3 | 4.11 | 3.06 | 2.75 | 2.7 | 3.19 | 3.67 | 3.72 | 3.73 | 52.34
e-Rudder | 13.62 | 6.16 | 7.58 | 6.52 | 6.08 | 7.95 | 9 | 8.1 | 8.21 | 8.54 | 7.51 | 10.05 | 99.32
Total | 86.75 | 44.54 | 56.72 | 52.72 | 50.04 | 47.77 | 45.22 | 44.6 | 60.08 | 71.39 | 67.72 | 67.15 | 694.7
Monthly values: output of eqmsn_2026.py on the Avances/Retards export of 07/10/2026 (rounded to 2 decimals). Total row and column are formulas.

## Standard
EqMSN 2026 per product (Standard)
Source: Tableau Avances / Retards export, 07/10/2026. 1 MSN = 1.0, spread evenly over calendar days from first milestone to OTA. Only work that falls inside 2026.
Produit | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Total
300VU | 0.44 | 0.52 | 0.78 | 0.69 | 0.72 | 0.59 | 0.94 | 0.85 | 1.65 | 1.41 | 1.12 | 0.92 | 10.63
740VU | 2.97 | 3.17 | 3.57 | 3.91 | 3.83 | 3.14 | 2.41 | 2.5 | 3.34 | 3.81 | 3.67 | 3.68 | 40
ISSF | 0.39 | 0.35 | 0.01 | 0.73 | 0.77 | 1.15 | 0.94 | 0.42 | 2.8 | 1.93 | 2.27 | 3.33 | 15.09
MDCD | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39 | 1.08 | 0.53 | 0 | 2.5
MFRL | 15.35 | 20.68 | 31.99 | 29.65 | 26.88 | 25.3 | 22.63 | 23.53 | 33.09 | 41.9 | 39.81 | 35.92 | 346.73
MIP | 6.86 | 6.48 | 7.15 | 6.45 | 6.19 | 5.39 | 5.28 | 5.3 | 6.2 | 7.59 | 7.8 | 8.12 | 78.81
MIP(2) | 0.66 | 0.61 | 0.63 | 0.57 | 0.77 | 0.68 | 0.64 | 0.69 | 0.51 | 0.64 | 0.67 | 0.72 | 7.79
OHP | 0.73 | 0.59 | 0.69 | 0.8 | 0.65 | 0.51 | 0.63 | 0.51 | 0.7 | 0.82 | 0.62 | 0.68 | 7.93
PTVU | 2.52 | 3.02 | 3.76 | 3.3 | 4.11 | 3.06 | 2.75 | 2.7 | 3.19 | 3.67 | 3.72 | 3.73 | 39.53
e-Rudder | 6.07 | 5.84 | 7.58 | 6.52 | 6.08 | 7.95 | 9 | 8.1 | 8.21 | 8.54 | 7.51 | 10.05 | 91.45
Total | 36.49 | 41.26 | 56.16 | 52.62 | 50 | 47.77 | 45.22 | 44.6 | 60.08 | 71.39 | 67.72 | 67.15 | 640.46
Monthly values: output of eqmsn_2026.py on the Avances/Retards export of 07/10/2026 (rounded to 2 decimals). Total row and column are formulas.

## Notes
How to read these tables
Unit | Each MSN counts as 1.0, spread evenly over the calendar days from its first milestone to its OTA. Data from the Avances/Retards export of 07/10/2026.
Adjusted vs Standard | Adjusted adds work done in 2025 on MSNs that ship in 2026 to their 2026 months. That is why January is high (86.75 Adjusted vs 36.49 Standard). Full year: 694.70 Adjusted vs 640.46 Standard. From June onward both tabs are identical.
Forecast months | MSNs still in progress use their planned OTA. MSNs not started yet use their planned dates. Oct–Dec are forecast, not actuals.
Out of scope | Work falling in 2027 is not counted in either tab.
Data corrections | 34 obvious date typos were corrected (wrong year, etc.) or replaced by the planned date. See the 'Data issues' tab.
To chase | 19 MSNs have a planned OTA that has already passed but no real OTA entered. Listed in 'Data issues' (Issue starts with 'no real OTA' or 'no real dates at all').
Which tab to use | Use Adjusted to see the whole load of MSNs shipping in 2026. Use Standard to see only the work that physically happened in 2026.

## Data issues
Dates corrected, ignored or estimated by the script
58 entries. 'Used' is the date the calculation used instead of the value in the file.
Produit | MSN | Rank | Milestone | Planned date | Value in file | Date used | Issue
MIP | 809 | 767 | Impression | 2025-10-14 | 14/10/2026 | 2025-10-14 | real date after export date -> year corrected
MFRL | 13588 | 359 | Impression | 2026-06-22 | 22/06/2025 | 2026-06-22 | 365 days from plan -> year corrected
MFRL | 13789 | 360 | Impression | 2026-06-22 | 22/06/2025 | 2026-06-22 | 365 days from plan -> year corrected
MFRL | 13719 | 361 | Impression | 2026-06-23 | 24/06/2025 | 2026-06-24 | 364 days from plan -> year corrected
MFRL | 13773 | 362 | Impression | 2026-06-23 | 24/06/2025 | 2026-06-24 | 364 days from plan -> year corrected
MFRL | 13372 | 200 | Enclenchement (SoA) | 2026-01-16 | 16/01/2025 | 2026-01-16 | 365 days from plan -> year corrected
MFRL | 13445 | 201 | Enclenchement (SoA) | 2026-01-19 | 19/01/2025 | 2026-01-19 | 365 days from plan -> year corrected
MFRL | 13388 | 202 | Enclenchement (SoA) | 2026-01-20 | 20/01/2025 | 2026-01-20 | 365 days from plan -> year corrected
MFRL | 13399 | 203 | Enclenchement (SoA) | 2026-01-21 | 21/01/2025 | 2026-01-21 | 365 days from plan -> year corrected
MFRL | 13492 | 204 | Enclenchement (SoA) | 2026-01-22 | 22/01/2025 | 2026-01-22 | 365 days from plan -> year corrected
MIP | 809 | 767 | SE | 2025-10-30 | 30/10/2026 | 2025-10-30 | real date after export date -> year corrected
MIP | 825 | 781 | INTE | 2026-02-03 | 12/12/2026 |  | real date after export date -> ignored, plan used
MIP | 827 | 782 | INTE | 2026-02-10 | 12/12/2026 |  | real date after export date -> ignored, plan used
PTVU | 2161 | 2095 | TEST | 2026-05-29 | 05/06/2025 | 2026-06-05 | 358 days from plan -> year corrected
740VU | 2146 | 2082 | TEST | 2026-02-05 | 05/02/0206 | 2026-02-05 | year out of range -> year corrected
MFRL | 12934 | 310 | TEST | 2026-05-18 | 18/05/2025 | 2026-05-18 | 365 days from plan -> year corrected
MFRL | 13735 | 314 | TEST | 2026-05-20 | 20/05/2025 | 2026-05-20 | 365 days from plan -> year corrected
MFRL | 13748 | 323 | TEST | 2026-05-28 | 28/05/2025 | 2026-05-28 | 365 days from plan -> year corrected
MFRL | 13796 | 354 | TEST | 2026-06-23 | 23/06/2025 | 2026-06-23 | 365 days from plan -> year corrected
e-Rudder | 13373 | 80 | TEST | 2026-06-12 | 12/0/2026 |  | year out of range -> ignored, plan used
MFRL | 13204 | 185 | Départ (OTA) | 2026-01-14 | 14/01/2025 | 2026-01-14 | 365 days from plan -> year corrected
MFRL | 13397 | 186 | Départ (OTA) | 2026-01-15 | 15/01/2025 | 2026-01-15 | 365 days from plan -> year corrected
MFRL | 13319 | 190 | Départ (OTA) | 2026-01-21 | 21/01/2025 | 2026-01-21 | 365 days from plan -> year corrected
MFRL | 13442 | 208 | Départ (OTA) | 2026-02-19 | 19/20/2026 |  | year out of range -> ignored, plan used
MFRL | 13413 | 210 | Départ (OTA) | 2026-02-23 | 23/02/0206 | 2026-02-23 | year out of range -> year corrected
MFRL | 13735 | 314 | Départ (OTA) | 2026-06-23 | 23/06/2025 | 2026-06-23 | 365 days from plan -> year corrected
MFRL | 13804 | 315 | Départ (OTA) | 2026-06-23 | 23/06/2025 | 2026-06-23 | 365 days from plan -> year corrected
MFRL | 13724 | 316 | Départ (OTA) | 2026-06-24 | 24/06/2025 | 2026-06-24 | 365 days from plan -> year corrected
MFRL | 13689 | 317 | Départ (OTA) | 2026-06-24 | 24/06/2025 | 2026-06-24 | 365 days from plan -> year corrected
MFRL | 13522 | 318 | Départ (OTA) | 2026-06-24 | 24/06/2025 | 2026-06-24 | 365 days from plan -> year corrected
MFRL | 13709 | 319 | Départ (OTA) | 2026-06-24 | 24/06/2025 | 2026-06-24 | 365 days from plan -> year corrected
e-Rudder | 13106 | 30 | Départ (OTA) | 2026-01-15 | 15/01/2025 | 2026-01-15 | 365 days from plan -> year corrected
e-Rudder | 13173 | 34 | Départ (OTA) | 2026-01-21 | 08/01/2025 | 2026-01-08 | 378 days from plan -> year corrected
e-Rudder | 12740 | 36 | Départ (OTA) | 2026-02-25 | 15/01/2025 |  | 406 days from plan -> ignored, plan used
MFRL | 13493 | 240 | span |  |  | 2026-03-12 | real milestone after OTA -> span extended to it
MFRL | 13578 | 241 | span |  |  | 2026-03-12 | real milestone after OTA -> span extended to it
MFRL | 14007 | 414 | span |  |  | 2026-09-15 | real milestone after OTA -> span extended to it
MDCD | 701 | 2 | Départ (OTA) | 2026-01-23 |  | 2026-01-23 | no real dates at all but planned OTA already past -> planned dates used
MDCD | 5106 | 3 | Départ (OTA) | 2025-12-08 |  | 2025-12-08 | no real dates at all but planned OTA already past -> planned dates used
PTVU | 2133 | 2068 | Départ (OTA) | 2025-10-31 |  | 2025-10-31 | no real OTA but planned OTA already past -> planned dates used
PTVU | 2140 | 2092 | Départ (OTA) | 2026-05-29 |  | 2026-05-29 | no real OTA but planned OTA already past -> planned dates used
PTVU | 2162 | 2096 | Départ (OTA) | 2026-06-29 |  | 2026-06-29 | no real OTA but planned OTA already past -> planned dates used
PTVU | 2172 | 2103 | Départ (OTA) | 2026-09-29 |  | 2026-09-29 | no real OTA but planned OTA already past -> planned dates used
740VU | 2166 | 2100 | Départ (OTA) | 2026-09-09 |  | 2026-09-09 | no real OTA but planned OTA already past -> planned dates used
740VU | 2167 | 2101 | Départ (OTA) | 2026-09-15 |  | 2026-09-15 | no real OTA but planned OTA already past -> planned dates used
740VU | 2168 | 2102 | Départ (OTA) | 2026-09-22 |  | 2026-09-22 | no real OTA but planned OTA already past -> planned dates used
740VU | 2172 | 2103 | Départ (OTA) | 2026-09-29 |  | 2026-09-29 | no real OTA but planned OTA already past -> planned dates used
MFRL | 13410 | 207 | Départ (OTA) | 2026-02-19 |  | 2026-02-19 | no real OTA but planned OTA already past -> planned dates used
MFRL | 13442 | 208 | Départ (OTA) | 2026-02-19 |  | 2026-02-19 | no real OTA but planned OTA already past -> planned dates used
MFRL | 13485 | 209 | Départ (OTA) | 2026-02-19 |  | 2026-02-19 | no real OTA but planned OTA already past -> planned dates used
MFRL | 13407 | 216 | Départ (OTA) | 2026-03-02 |  | 2026-03-02 | no real OTA but planned OTA already past -> planned dates used
MFRL | 13686 | 301 | Départ (OTA) | 2026-06-05 |  | 2026-06-05 | no real OTA but planned OTA already past -> planned dates used
e-Rudder | 12740 | 36 | Départ (OTA) | 2026-02-25 |  | 2026-02-25 | no real OTA but planned OTA already past -> planned dates used
e-Rudder | 13248 | 49 | Départ (OTA) | 2026-05-11 |  | 2026-05-11 | no real OTA but planned OTA already past -> planned dates used
OHP | 166 | 165 | Départ (OTA) | 2026-09-28 |  | 2026-09-28 | no real OTA but planned OTA already past -> planned dates used
300VU | 165 | 164 | Départ (OTA) | 2026-09-16 |  | 2026-09-16 | no real OTA but planned OTA already past -> planned dates used
MFRL | 13667 | 285 | block |  |  |  | duplicate MSN block -> second copy dropped
(all) | 57 blocks | [5 empty] | no planned or real dates -> excluded